## Conference Project Plan
MEGA PROJECT PLAN
PROJECT STAGES: | STAGE ACTIVITIES:
Registration & Attendee Management
Responsible: |  | Identify key stakeholders | 100%
|  | Conduct market research | 100%
Start Date: 2025-03-01 |  | Define conference goals and objectives | 100%
End Date: 2025-03-14 |  | Develop initial budget | 100%
Registration & Attendee Management
Responsible: |  | Select conference venue | 100%
|  | Arrange accommodation for participants | 100%
Start Date: 2025-03-15 |  | Plan transportation and parking logistics | 75%
End Date: 2025-04-11 |  | Coordinate with venue for catering and AV | 50%
Marketing & Promotion
Responsible: |  | Develop marketing strategy | 30%
|  | Design promotional materials | 0%
Start Date: 2025-03-29 |  | Launch social media campaign | 0%
End Date: 2025-03-14 |  | Send out invitations and press releases | 0%
Content & Program Development
Responsible: |  | Recruit speakers and panelists | 0%
|  | Develop conference schedule and agenda | 0%
Start Date: 2025-04-12 |  | Design session formats | 0%
End Date: 2025-04-25 |  | Create conference materials | 0%
Registration & Attendee Management
Responsible: |  | Set up registration system | 0%
|  | Manage attendee communication | 0%
Start Date: 2025-04-26 |  | Track and confirm registrations | 0%
End Date: 2025-05-09 |  | Prepare attendee materials | 0%
Execution & Post-Event Activities
Responsible: |  | Oversee conference day(s) operations | 0%
|  | Coordinate with volunteers and staff | 0%
Start Date: 2025-05-10 |  | Conduct post-event surveys and feedback | 0%
End Date: 2025-05-24 |  | Prepare post-event report and analysis | 0%