## Research Project Plan
RESEARCH PROJECT PLAN
Comprehensive Multivariate Analysis
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
JAN | bar: 20 to 31
FEB | bar: 1 to 7; 10 to 28
MAR
APR | bar: 14 to 30
MAY | bar: 1 to 9
JUN | bar: 2 to 20
JUL
AUG
SEP | bar: 8 to 26
OCT
NOV | bar: 3 to 24
DEC
| Research Phase #1 | 4: Research Phase #2; 10: Research Phase #3; 16: Research Phase #4; 22: Research Phase #5; 28: Research Phase #6
Data Collection |  | 3: Data Cleaning; 9: Exploratory Analysis; 15: Model Development; 21: Model Evaluation; 27: Reporting Results
JAN 20 - FEB 07, 2025 |  | 3: FEB 10 - FEB 28, 2025; 9: APR 14 - MAY 09, 2025; 15: JUN 02 - JUN 20, 2025; 21: SEP 08 - SEP 26, 2025; 27: NOV 03 - NOV 24, 2025
Gather diverse and relevant data from surveys, experiments, and databases. Ensure thoroughness for comprehensive datasets and future analysis requirements. |  | 3: Process collected data by identifying and removing duplicates, correcting errors, and managing missing values. Maintain data integrity and consistency throughout.; 9: Conduct an initial analysis to uncover patterns, trends, and anomalies. Use visualizations and summary statistics to generate early insights and hypothesis validation.; 15: Create predictive models utilizing advanced ML algos. Conduct rigorous training and validation, focusing on enhancing model accuracy and performance metrics.; 21: Evaluate model performance using various metrics like accuracy, precision, recall, and F1 score. Implement cross-validation techniques and refine model robustness.; 27: Synthesize and compile research findings into a comprehensive report. Include detailed visualizations and actionable insights for stakeholder presentations.